Master Project Plan: "Nexus" - From MVP to Full Scale

Project Manager: Osvaldo Rizzi Junior

Total Timeline: 9 Weeks (1 Week MVP + 8 Weeks Evolution)

Core Objective: Launch a functional P2P sync tool in 5 days, then evolve it into a collaborative, cross-platform workspace.

📅 Phase 1: The MVP (Tactical Sprint)

Timeline: Days 1-5 (Monday - Friday)

Goal: Ship a working Command Line Interface (CLI) that synchronizes a folder between two computers over the internet.

Constraint: No GUI, Single-Writer only.

Day 1: Infrastructure & Networking

- Objective: Two terminals on different networks find each other.

- Tasks:

  - Initialize Pear project; install hyperswarm, corestore, bare-process.

  - Host Logic: Generate topic key, join swarm, log "Listening".

  - Client Logic: Accept key input, join swarm, log "Connected".

  - Deliverable: Successful handshake between Peer A and Peer B.

Day 2: The Virtual Drive

- Objective: Write data to the P2P encryption layer.

- Tasks:

  - Integrate Hyperdrive with Corestore.

  - Host: Create drive, write dummy file programmatically.

  - Client: Replicate stream, read dummy file.

  - Deliverable: Client prints content of a file existing only in the Host's RAM/DB.

Day 3: File System Mirroring

- Objective: Connect P2P layer to real OS files.

- Tasks:

  - Integrate localdrive (OS folder wrapper) and mirror-drive.

  - Host: mirror(localdrive, hyperdrive, { live: true }).

  - Client: mirror(hyperdrive, localdrive, { live: true }).

  - Deliverable: Creating a file on Host Desktop instantly appears on Client Desktop.

Day 4: Resilience & UX

- Objective: Make it a usable tool.

- Tasks:

  - CLI Args: Handle --dir, --mode, and --key.

  - Feedback: Log specific sync events ([SYNC] Downloading report.pdf...).

  - Reconnection: Verify auto-reconnect on WiFi toggle.

Day 5: QA & Release 1.0

- Objective: Validation and Deploy.

- Tasks:

  - LAN Test: Sync 500MB video file.

  - WAN Test: Sync text file between WiFi and 4G Hotspot (NAT Traversal).

  - Documentation: Write README.md with setup instructions.

  - Milestone: DEPLOY MVP v0.1 to internal users.

🚀 Phase 2: Post-MVP Evolution (Strategic Roadmap)

Timeline: Weeks 2-9 (4 Sprints of 2 Weeks) Goal: Transition from a "Backup Tool" to a "Collaborative Workspace" with GUI and Mobile support.

Sprint 1: The Collaboration Engine (Weeks 2-3)

Focus: Multi-Writer Architecture

- Goal: Enable bi-directional editing (Peer A and Peer B edit same folder).

- Key Tasks:

  - Autobase Integration: Replace standard Hyperdrive with Autobase to handle multi-user operation logs (oplogs).

  - Conflict Strategy: Implement "Latest Writer Wins" or "Conflict Forking" (creating file_conflicted_copy.txt).

- Deliverable: Bi-directional sync where both parties can write.

Sprint 2: The Desktop Experience (Weeks 4-5)

Focus: User Experience (GUI)

- Goal: Replace CLI with a native-feeling Desktop App.

- Key Tasks:

  - Pear Desktop: Initialize HTML/CSS/JS frontend within Pear.

  - Drive Manager: Sidebar UI to list synced drives.

  - Visual Feedback: Progress bars instead of console logs.

  - Identity Export: Settings screen to save/load private keys.

- Deliverable: .dmg / .exe installer launching a windowed app.

Sprint 3: The Mobile Foundation (Weeks 6-7)

Focus: Mobile Infrastructure

- Goal: Port the P2P stack to iOS/Android.

- Key Tasks:

  - Bare-Expo: Initialize mobile project structure.

  - Port Logic: Adapt core sync logic for mobile constraints (TCP/UDP handling).

  - Mobile Storage: Map Hyperdrive to phone's internal scoped storage.

- Deliverable: Headless mobile app receiving files from Desktop.

Sprint 4: Mobile Polish & Ecosystem (Weeks 8-9)

Focus: Mobile UI & QA

- Goal: Full mobile browsing and previewing.

- Key Tasks:

  - React Native UI: File list and grid views.

  - Sparse Downloading: Implement "On-Demand" loading (stream file only when clicked).

  - Cross-Platform QA: Test sync cycle: Desktop -> Mobile -> Desktop.

- Deliverable: DEPLOY v1.0 (Desktop + Mobile Beta).

📦 Resource & Stack Summary

Technical Stack

- Runtime: pear (Desktop), bare-expo (Mobile).

- Networking: hyperswarm (DHT).

- Storage: corestore, hyperdrive, autobase (Sprint 1+).

- Sync: localdrive, mirror-drive.

Team Allocation

- Phase 1 (MVP): 1 Backend/P2P Specialist.

- Phase 2 (Sprint 1-2): +1 Frontend Developer (React).

- Phase 2 (Sprint 3-4): +1 Mobile Developer (React Native), +1 QA Specialist.

Risk Management

- NAT Traversal: If MVP fails on 4G, implement Relay Server fallback in Phase 2.

- Mobile Backgrounding: Mobile OS kills background sync. Mitigation: "Wake Service" or "Foreground-only Sync" policy.

- Data Conflicts: Autobase complexity is high. Mitigation: Allocating full 2 weeks to Sprint 1.